**2018-19 Student Equity Plan and Vision for Success Timeline**

March 14 – College Planning Committee meets and starts discussion around setting institutional metrics for Equity Plan and Vision for Success

March 19 – College Planning Committee meets again to continue updates of institutional metrics for Equity Plan and Vision for Success

By March 29 – Ola to update all data needed for Equity Plan

April 9 or 11 – College Planning Committee finalize metrics based on Ola’s report of Disproportionately Impacted populations that need a separate goal in Equity Plan

Week of April 15 – Convene the Integrated Plan Team (Equity + 3SP + BSI) to review and approval Equity Plan

Through April 26 – Mallory and Lorrie share updated institutional metrics, Equity Plan, and Vision for Success goals with governance groups for feedback: Academic Senate; Classified Senate; SSPBT; IPBT; FCOPBT; EAC; College Council

No later than April 30th at 9 a.m. – Submit plans to Pippa/Paula for BoardDocs posting

May 6 – Vision for Success Goals and Equity Plan go to Board of Trustees for approval

May 31 – Submit Vision for Success Goals

June 30 – Submit Equity Plan